## Participants
Inspection Roles
No | Group Member | Roles | Comment
1 | Ngo Thi Tuyet Nhung | Moderator
2 | Huynh Thi My Duyen | Inspector
3 | Nguyen Van Dung | Inspector
4 | Ngo Nguyen Truong An | Inspector
5 | Truong Tan Loc | Inspector
6 | Team 1 | Author

## Schedule
Inspection Schedule
No | Task | Task owner | Start time | End time | Comment
1 | Divide the roles of each member within the team | Nhung | 2024-01-27 | 2024-01-27
2 | Receive materials from team 1 | Nhung | 2024-01-27 | 2024-01-27
3 | Make plan schedule for team | Nhung | 2024-01-27 | 2024-01-28
4 | Distribute documents to other members in the team | Nhung | 2024-01-27 | 2024-01-28
5 | Inspect Planning and Defined Process Document | Nhung | 2024-01-28 | 2024-01-28
6 | Inspect SRS Document | Nhung | 2024-01-28 | 2024-01-28
7 | Inspect UI Design Document | Dung | 2024-01-28 | 2024-01-28
8 | Inspect Code | Dung | 2024-01-28 | 2024-01-28
9 | Inspect Test-Case file | An | 2024-01-28 | 2024-01-28
10 | Inspect Definded Process Document file | Loc | 2024-01-28 | 2024-01-28
11 | Inspect Planning Document file | Duyen | 2024-01-28 | 2024-01-28
12 | Integration all inspection files | Nhung | 2024-01-28 | 2024-01-29
13 | Finish the first inspection | Nhung, Duyen, Dung, An, Loc | 2024-01-29 | 2024-01-29

## Material
Inspection Material
No | Tool/Material | Quantity | Comment
1 | Defined Process Document | 1 | Loc
2 | Project Plan Document | 1 | Duyen
3 | Software Requirement Specification Document | 1 | Nhung
4 | User Interface Design Document | 1 | Dung
5 | Code Java | 1 | Dung
6 | Test-Case | 1 | An